## 00_README
UHPC BEAM CDP ¦ MODEL COMPARISON & ABAQUS RUN PLAN ¦ V2
Design | 12 experimental T-beams; 4 screening specimens, 8 pre-designated within-study holdout specimens.
Recommended executable 3D jobs | 42 core planned; 2 HSS conditional HOLD; none executed.
Material unit tests | Optional 3 batches x (4 compression + 2 tension)=18 one-element constitutive QA; NOT counted as 3D beam jobs.
Source primary | https://doi.org/10.1016/j.engstruct.2025.121810
Source methods | https://doi.org/10.1016/j.engstruct.2025.120154
Tensile choice | T1 Tian 2023 as modified by Fakeh 2025; T2 Zhao 2013. Post-cracking use stress-cracking displacement, not raw engineering stress-strain.
Compressive choice | C1 Modified Graybeal is initial baseline; C2 Zhao, C3 Wang, C4 Yan as alternative published expressions summarized in Fakeh Table 3.
Plan policy | Sequential screening: P1 fixes C1, P2 fixes T_BEST; full 2x4 interaction NOT tested. If models interact, authorize extra cross-over jobs before validation.
Holdout policy | Do NOT look at holdout FE fit to retune constitutive laws; holdout = within-study only, not external study independent validation.
Geometry flag | B11 has different support arrangement. Source Fig 1 must be implemented separately; do not force generic support.
Rebar flag | Top bars #3 vs #4 ambiguity in article picture/text: needs primary-figure verification; no silent assumption.
Batch 2 flag | Mean Ec=47.3 GPa, fc=153.2 MPa and strain peak .0032 leads slightly negative nominal compression inelastic strain at peak; require physical repair/evidence audit before CDP table.
HSS flag | Steel hardening strain path not fully reported; do not invent law from fy and fu alone.
Mesh flag | 15 / 20 / 30 mm are proposed design levels, NOT literature-reported values; sufficient element quality + hourglass + load/energy checks required.
Damage flag | dt/dc not identified uniquely from monotonic envelopes. Do not invent damage parameters or use damage laws without a documented rule.
Status | PLAN ONLY / ZERO ABAQUS EXECUTIONS

## 01_SAMPLES
Sample ID | Original specimen ID (normalized) | Vf (%) | Batch ID | Stirrup | rho_sv (%) | a/d | Vult_exp (kN) | Delta_peak_exp (mm) | Failure mode | Cohort | Source | Special notes
B01 | Vf1-rho0-1.7 | 1 | 3 | NONE | 0 | 1.7 | 884 | 7.9 | DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B02 | Vf1-rho0-2.7 | 1 | 3 | NONE | 0 | 2.7 | 478 | 12.7 | DT | SCREEN | https://doi.org/10.1016/j.engstruct.2025.121810
B03 | Vf2-rho0-1.7 | 2 | 2 | NONE | 0 | 1.7 | 1241 | 14.6 | DC+SC | SCREEN | https://doi.org/10.1016/j.engstruct.2025.121810
B04 | Vf2-rho0-2.7 | 2 | 2 | NONE | 0 | 2.7 | 862 | 29.6 | DT+DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B05 | Vf1-rho0.6N-1.7 | 1 | 3 | NSS | 0.6 | 1.7 | 1358 | 14.1 | DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B06 | Vf1-rho0.6N-2.7 | 1 | 3 | NSS | 0.6 | 2.7 | 888 | 30 | DT+DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B07 | Vf2-rho0.6N-1.7 | 2 | 1 | NSS | 0.6 | 1.7 | 1534 | 18.9 | DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B08 | Vf2-rho0.6N-2.7 | 2 | 1 | NSS | 0.6 | 2.7 | 1092 | 38.9 | DT+DC+SC | SCREEN | https://doi.org/10.1016/j.engstruct.2025.121810
B09 | Vf1-rho0.7H-1.7 | 1 | 3 | HSS | 0.7 | 1.7 | 1600 | 15.8 | DC+SC | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B10 | Vf1-rho0.7H-2.7 | 1 | 3 | HSS | 0.7 | 2.7 | 1156 | 35.9 | DC+FL | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810
B11 | Vf1-rho0.4H-2.7 | 1 | 3 | HSS | 0.4 | 2.7 | 1125 | 23.1 | DC+FL | VALIDATION | https://doi.org/10.1016/j.engstruct.2025.121810 | Special support arrangement in Fig 1
B12 | Vf1-rho0.5H-2.7 | 1 | 3 | HSS | 0.5 | 2.7 | 1134 | 38.3 | DC+FL | SCREEN | https://doi.org/10.1016/j.engstruct.2025.121810

## 02_MATERIAL_LAWS
Model ID | Mode | Reference | Response | Implementation | Priority | Origin URL | Data availability / caution
T1_TIAN_FAKEH | TENSION | Tian et al. 2023 + Fakeh et al. 2025 | Two-stage rising + linear descending extension and residual stress | Pre-localization sigma-eps; post-localization sigma-w via validated crack displacement | PRIMARY | https://doi.org/10.1016/j.engstruct.2025.120154 ¦ https://doi.org/10.1016/j.conbuildmat.2023.131634 | Use batch f_t and critical strains; conversion depends on characteristic length and crack mechanics.
T2_ZHAO | TENSION | Zhao et al. 2013 as compared in Fakeh 2025 | Elastic + tensile hardening + power-law softening | Convert post-crack to crack displacement with explicit regularization | COMPARATOR | https://doi.org/10.1016/j.engstruct.2025.120154 ¦ https://doi.org/10.1016/j.conbuildmat.2013.07.061 | No universal postpeak Gf value; avoid misleading area under sigma-eps as a mesh-objective fracture energy.
C1_GRAYBEAL_FAKEH | COMPRESSION | Graybeal 2007 + Prem et al. 2015 modified by Fakeh 2025 | Nonlinear ascending + added descending line | Convert to compression hardening sigma-eps_inel, check monotonicity | PRIMARY | https://doi.org/10.1016/j.engstruct.2025.120154 | Post-peak added by Fakeh (not part of original Graybeal model).
C2_ZHAO | COMPRESSION | Zhao et al. 2013 | Ascending near elastic + descending | Compression hardening with E from actual batch | COMPARATOR | https://doi.org/10.1016/j.engstruct.2025.120154 ¦ https://doi.org/10.1016/j.conbuildmat.2013.07.061 | Enforce stress continuity and nonnegative inelastic strain.
C3_WANG | COMPRESSION | Wang et al. 2016 | Parabolic ascending; residual descending | Compression hardening with measured Ec consistency | COMPARATOR | https://doi.org/10.1016/j.engstruct.2025.120154 | Expression originally for a different member/material context; do not treat as empirically confirmed for Hosseini batches.
C4_YAN | COMPRESSION | Yan 2010 | Rational ascending/descending | Compression hardening | COMPARATOR | https://doi.org/10.1016/j.engstruct.2025.120154 | Verify equation OCR against Fakeh Table 3 image before generation.

## 03_RUN_MATRIX
Job ID | Stage | Specimen | Tension law | Compression law | Mesh h (mm) | psi (deg) | fb0/fc0 | e | Kc | mu | Steel model | Gate | Only changed field | Purpose | Status | Sources
UHPC_001 | P1_TENSION_SCREEN | B02 | T1_TIAN_FAKEH | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_002 | P1_TENSION_SCREEN | B02 | T2_ZHAO | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_003 | P1_TENSION_SCREEN | B03 | T1_TIAN_FAKEH | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_004 | P1_TENSION_SCREEN | B03 | T2_ZHAO | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_005 | P1_TENSION_SCREEN | B08 | T1_TIAN_FAKEH | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_006 | P1_TENSION_SCREEN | B08 | T2_ZHAO | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_007 | P1_TENSION_SCREEN | B12 | T1_TIAN_FAKEH | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_008 | P1_TENSION_SCREEN | B12 | T2_ZHAO | C1_GRAYBEAL_FAKEH | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_1 | Tension model only | T1/T2 with C1 on four contrasting mechanisms | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_009 | P2_COMPRESSION_SCREEN | B02 | T_BEST_LOCKED | C2_ZHAO | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_010 | P2_COMPRESSION_SCREEN | B02 | T_BEST_LOCKED | C3_WANG | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_011 | P2_COMPRESSION_SCREEN | B02 | T_BEST_LOCKED | C4_YAN | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_012 | P2_COMPRESSION_SCREEN | B03 | T_BEST_LOCKED | C2_ZHAO | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_013 | P2_COMPRESSION_SCREEN | B03 | T_BEST_LOCKED | C3_WANG | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_014 | P2_COMPRESSION_SCREEN | B03 | T_BEST_LOCKED | C4_YAN | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_015 | P2_COMPRESSION_SCREEN | B08 | T_BEST_LOCKED | C2_ZHAO | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_016 | P2_COMPRESSION_SCREEN | B08 | T_BEST_LOCKED | C3_WANG | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_017 | P2_COMPRESSION_SCREEN | B08 | T_BEST_LOCKED | C4_YAN | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_018 | P2_COMPRESSION_SCREEN | B12 | T_BEST_LOCKED | C2_ZHAO | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_019 | P2_COMPRESSION_SCREEN | B12 | T_BEST_LOCKED | C3_WANG | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_020 | P2_COMPRESSION_SCREEN | B12 | T_BEST_LOCKED | C4_YAN | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_2 | Compression model only | Only after best tensile model frozen from P1 | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_021 | P3_HOLDOUT_8 | B01 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_022 | P3_HOLDOUT_8 | B04 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_023 | P3_HOLDOUT_8 | B05 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_024 | P3_HOLDOUT_8 | B06 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_025 | P3_HOLDOUT_8 | B07 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_026 | P3_HOLDOUT_8 | B09 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_027 | P3_HOLDOUT_8 | B10 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_028 | P3_HOLDOUT_8 | B11 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_3 | Specimen only | No retrospective tuning based on these samples | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_029 | P4_MESH_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 15 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_030 | P4_MESH_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 30 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_031 | P4_MESH_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 15 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_032 | P4_MESH_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 30 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_033 | P4_MESH_CHECK | B12 | T_BEST_LOCKED | C_BEST_LOCKED | 15 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_034 | P4_MESH_CHECK | B12 | T_BEST_LOCKED | C_BEST_LOCKED | 30 | 55 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_4 | Mesh only | Compare to previously run 20-mm baseline | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_035 | P5_PSI_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 35 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Dilation angle only | 55deg base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_036 | P5_PSI_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 45 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Dilation angle only | 55deg base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_037 | P5_PSI_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 35 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Dilation angle only | 55deg base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_038 | P5_PSI_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 45 | 3 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Dilation angle only | 55deg base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_039 | P5_FB0_FC0_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 1.16 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Stress ratio only | 3.0 base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_040 | P5_FB0_FC0_CHECK | B02 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 2 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Stress ratio only | 3.0 base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_041 | P5_FB0_FC0_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 1.16 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Stress ratio only | 3.0 base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_042 | P5_FB0_FC0_CHECK | B08 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 2 | 0.1 | 0.66667 | 0 | STEEL_BASE | GATE_5 | Stress ratio only | 3.0 base already run | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_043 | P6_HSS_CONDITIONAL | B10 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | HSS_PERFECT_PLASTIC | HOLD_NEEDS_STEEL_HARDENING | HSS law only | Diagnostic vs measured/defensible hardening law; NOT approved until strain-hardening law is evidenced | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154
UHPC_044 | P6_HSS_CONDITIONAL | B12 | T_BEST_LOCKED | C_BEST_LOCKED | 20 | 55 | 3 | 0.1 | 0.66667 | 0 | HSS_PERFECT_PLASTIC | HOLD_NEEDS_STEEL_HARDENING | HSS law only | Diagnostic vs measured/defensible hardening law; NOT approved until strain-hardening law is evidenced | PLANNED_NOT_RUN | https://doi.org/10.1016/j.engstruct.2025.121810 ¦ https://doi.org/10.1016/j.engstruct.2025.120154

## 04_STAGE_COUNTS
Stage | Number of planned 3D runs | Execution policy | Boundary / reuse
P1_TENSION_SCREEN | 8 | CORE | 4 specimens x 2 tension laws; fixed C1
P2_COMPRESSION_SCREEN | 12 | CORE_AFTER_GATE_1 | 4 specimens x 3 alternative compression laws; selected T1 or T2 frozen; C1 from P1 is reused
P3_HOLDOUT_8 | 8 | CORE_AFTER_GATE_2 | 8 specimens x selected locked material pair; 4 screened models reused
P4_MESH_CHECK | 6 | CORE_AFTER_GATE_3 | 3 specimens x 2 additional mesh levels; baseline 20mm preexisting
P5_PSI_CHECK | 4 | CORE_AFTER_GATE_3 | 2 specimens x 2 alternative psi levels; 55deg baseline reused
P5_FB0_FC0_CHECK | 4 | CORE_AFTER_GATE_3 | 2 specimens x 2 alternative ratio levels; 3.0 baseline reused
P6_HSS_CONDITIONAL | 2 | CONDITIONAL_HOLD | 2 HSS specimens x idealized steel alternate; require measured/defensible hardening baseline
TOTAL_CORE | 42 | PLANNED / NOT RUN | Excludes 2 HSS conditional jobs
TOTAL_WITH_CONDITIONAL | 44 | PLANNED / NOT RUN | 2 HSS conditional jobs remain HOLD
FULL_FACTORIAL_12x2x4 | 96 | NOT RECOMMENDED | Not a required program; no complete 2x4 across all 12 specimens

## 05_BATCHES
Batch | Vf (%) | fc (MPa) | Ec (GPa) | eps_cp (fraction) | ft_cr (MPa) | eps_t_cr (fraction) | ft_loc (MPa) | eps_t_loc (fraction) | Nominal compressive inelastic at peak | Source | Flag
1 | 2 | 152.8 | 46 | 0.0035 | 9 | 0.0016 | 10 | 0.005 |  | https://doi.org/10.1016/j.engstruct.2025.121810
2 | 2 | 153.2 | 47.3 | 0.0032 | 8.8 | 0.0015 | 9.3 | 0.005 |  | https://doi.org/10.1016/j.engstruct.2025.121810
3 | 1 | 166.4 | 45.4 | 0.004 | 6 | 0.001 | 7.5 | 0.0027 |  | https://doi.org/10.1016/j.engstruct.2025.121810

## 06_GATES
Gate | Required evidence / conditions | Decision
GATE_0 | Article Fig 1 geometry support, steel bar ambiguity, 3 batches data audited; 3 constituent CDP input files consistent; unit conversion validated | HOLD
GATE_1 | Four pilot beams run under C1 with T1/T2, evaluate curve shape peak, crack localization and failure mode; choose and freeze one tension law | HOLD
GATE_2 | Compare four compression law options on same four pilot beams with T_BEST; lock a single global constitutive-law type and batch-specific inputs | HOLD
GATE_3 | Run eight untouched holdout specimens. Report same-study held-out error, not external validation. No tuning to holdout. | HOLD
GATE_4 | Check mesh / hourglass / artificial energy / shear localization for B02 B08 B12 at h 15 20 30; test objectivity | HOLD
GATE_5 | Sensitivity psi and fb0/fc0 using independently fixed constitutive law; do not select solely to optimize peak | HOLD
GATE_6 | Optional HSS steel law test only with defensible post-yield strain measurements or explicit bounded assumptions | HOLD
REQUIRED OUTPUT | reaction RF vs deflection at actual gauges; peak V; delta_peak; stiffness; damage/crack location; compression strut damage; energy histories; mesh diagnostics | HOLD
NO AUTOMATIC SUBMIT | Register is a plan; Abaqus jobs have not been created/submitted. Any release requires source/rebar/support reconciliation. | HOLD